## 4800131518
116972 B-TECH ENGINEERING- bill details - GD-SEZ , Airoli
PO No | Description of work | HSN/SAC | PO Qty | Unit | Rate | PO Amount | Quantity |  |  | Bill Amount |  |  | Remark | Act Qty | Act Amount | % | CHALLAN NO.
[7 empty] | Previous | This Bill | Uptodate | Previous | This Bill | Uptodate
4800131518 | Ser - PHE Works
10 | PITC of CPVC pipe- 15 mm dia | 995462 | 5 | M | 190 | 950 | 3 | 2 | 5 | 570 | 380 | 950 | - | 5 | 950 | 100% | 19035/1
20 | PITC of CPVC Pipe - 20 mm dia | 995462 | 35 | M | 250 | 8750 | 21 | 14 | 35 | 5250 | 3500 | 8750 | - | 35 | 8750 | 100% | 19035/2
30 | PITC of CPVC Pipe - 25 mm dia | 995462 | 45 | M | 350 | 15750 | 27 | 18 | 45 | 9450 | 6300 | 15750 | - | 45 | 15750 | 100% | 19035/3
40 | PITC of Forged Brass Ball Valve -20mm | 995462 | 5 | NOS | 660 | 3300 | 3 | 2 | 5 | 1980 | 1320 | 3300 | - | 5 | 3300 | 100% | 19035/4
50 | PITC of Forged Brass Ball Valve -25 mm | 995462 | 1 | NOS | 845 | 845 | 0.6 | 0.4 | 1 | 507 | 338 | 845 | - | 1 | 845 | 100% | 19035/5
60 | PITC of Water Meter | 995462 | 5 | NOS | 3700 | 18500 | 3 | 2 | 5 | 11100 | 7400 | 18500 | - | 5 | 18500 | 100% | 19052/1
70 | PITC of PRV Station- 25 mm dia | 995462 | 1 | NOS | 4500 | 4500 | 0.6 | 0.4 | 1 | 2700 | 1800 | 4500 | - | 1 | 4500 | 100% | 19035/6
80 | PITC of UPVC Pipe - 6 kg -110 mm dia | 995462 | 10 | M | 540 | 5400 | 6 | 4 | 10 | 3240 | 2160 | 5400 | - | 10 | 5400 | 100% | 19035/7
90 | PITC of UPVC Pipe - 6 kg -160 mm dia | 995462 | 30 | M | 1350 | 40500 | 18 | 12 | 30 | 24300 | 16200 | 40500 | - | 30 | 40500 | 100% | 19035/8
100 | PITC of PVC Gully Trap | 995462 | 3 | NOS | 4500 | 13500 | 1.8 | 1.2 | 3 | 8100 | 5400 | 13500 | - | 3 | 13500 | 100% | 19035/9
110 | PITC of Multi Floor Trap | 995462 | 5 | NOS | 1250 | 6250 | 3 | 2 | 5 | 3750 | 2500 | 6250 | - | 5 | 6250 | 100% | 19035/10
120 | PITC of PVC Nahani Trap 110 mm dia | 995462 | 1 | NOS | 550 | 550 | 0.6 | 0.4 | 1 | 330 | 220 | 550 | - | 1 | 550 | 100% | 19035/12
[6 empty] | 118795 |  |  |  | 71277 | 47518 | 118795 |  |  | 118795
| CGST 0% |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  | 0
| SGST 0% |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  | 0
[6 empty] | 118795 |  |  |  | 71277 | 47518 | 118795 |  |  | 118795
[11 empty] | 28510.8 | 71277
-
| Total |  |  |  |  | 118795 |  |  |  | 71277 | 47518 | 118795
12) Terms of Payment:
a)Secured Advance/Advance Against Material At Site:
60% of BOQ item rate will be paid against material delivery at site as an advance against request letter on Contractor Company Letter head will be recoverable on Pro-rata basis.
Contractor need to take prior schedule approval from Owner's Engineer In Charge before material delivery at site.
b) Running Account Bills:
1. 90% against Installation (tax invoice on completion of Installation, will be raised by vendor on pro-rata basis)."Payment will be made within 30 working days from the date of submission of technically correct invoice along with all the compliance supporting documents in original." after deducting all advances/other dues etc.
2. 10% against testing, successful commissioning & handing over to the owner along with necessary documentations.
The contractor shall be paid only for the completed items.
All the bill to be submitted by the contractor shall be TAX
INVOICE clearly mentioning the applicable tax amounts.
Fortnightly bills shall be raised by the contractor. Payment will be made within 30 working days from the date of submission of technically correct invoice along with all the compliance supporting documents in original.
Final bill shall be scrutinized and settled within 30 days after submission of technically correct invoice along with all the compliance supporting documents in original.
c) Retention money:
05% of the value of work done for each running and final bill will be deducted and retained as retention money, which will be released after the satisfactory completion of the defect's liability period.

## Bill Details (hidden)
101864 STERLING & WILSON
PO No | Bill No | Date of Bill | Miro No | Bill Amount | WCT | TDS | E Cess | H Ed Cess | Adv | Elect charges | Add Retention | security deposit | Insurance | Retention | Debits | Paid Amount | Cheque No | Date | Remark
4800116480 | Advance against BG | 02.05.2018 | [6 empty] | -689047 | 0 |  |  | 0 | 0 |  | 689047 |  |  | 03.05.2018
0
0
BG NO - 49580IGL0026318 dt 23.04.2018
BG amount Rs 6,89,047
Validity upto 05.10.2018
Union Bank Of India
|  |  | Total | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 689047
21A)TERMS OF PAYMENT
1. 10% mobilisation advance will be paid against a Bank Guarantee for equivalent amount in approved format from a Nationalised /Scheduled bank valid from the date of commencement of the project valid till three months beyond completion period. This advance will be so recovered progressively from your running bills that the entire amount of advance is recovered by the time 80% of the contract value is paid to you.
2. 60 % against delivery of contractors materials at site on pro rata basis through RTGS. Advance Invoice will be accepted against Providing of contractors material & advance will be given against the same.
3. 30% against Installation of HVAC Low Side system.
4. 10 % against successful testing, commissioning & handing over of the system.
5. 5% of the value of the work done for each running bill will be deducted and retained in cash as retention money which will be released after submission bank guarantee after handing over of the project valid upto defects liability period.
*BG need to be submitted during final invoice.
TDS towards income tax & GST as applicable shall be deducted from each & every Tax Invoice raised at the rates, prevailing from time to time.
Interim bill payment will be cleared within 21 working days after submission of the technically correct bill along with the relevant documents.
All the bills have to be certified by the Project Architect/ Consultants/ Project In Charge before making any payments.

## cer (hidden)
PAYMENT SUMMARY/ADVICE
WORK ORDER NO. : | 4800116480 |  |  |  | DEBIT TO SOCIETY/APEX BODY
PROFIT CENTER : | 1150011301
CUSTOMER CODE:
PLANT: | SERENE PROPERTIES PVT. LTD., BLDG NO 3( C010)
VENDOR CODE /NAME: | 101864 STERLING & WILSON
NAME OF SOCIETY:
COMPANY CODE: | 1150 | advance against Bank Guarantee
| PERIOD: |  | To | 02.05.2018 | PO Amt |  | 6890470
PARTICULARS |  | REF.DOC. NO. | SAP.DOC. NO. | DOCUMENT | POSTING | TDS | AMOUNT RS.
| ADVANCE REQUEST | against Bank Guarantee |  |  |  |  | 689047
| RETENTION RELEASE | BG NO - 49580IGL0026318 dt 23.04.2018 |  |  |  |  | 0
BG amount Rs 6,89,047
Validity upto 05.10.2018
| VENDOR INVOICE -CERTIFIED AMOUNT | Union Bank Of India |  |  |  |  | 0
LESS: | SALE OF MATERIALS | [5 empty] | 0
LESS: | SALE OF EMPTY CEMENT BAGS | [5 empty] | 0
LESS: | RENTAL CHARGES FOR SCAFF/MACHIENERY | [5 empty] | 0
LESS: | WATER CHARGES RECOVERY | [5 empty] | 0
LESS: | ELECTRICITY CHARGES RECOVERY | [5 empty] | 0
LESS: | INSURANCE CHARGES RECOVERY | [5 empty] | 0
LESS: | OTHER RECOVERIES | [5 empty] | 0
[6 empty] | Rs. | 0
LESS: | RETENTION AMOUNT | [5 empty] | 0
LESS: | ADVANCE TO BE ADJUSTED | [5 empty] | 0
[6 empty] | Rs. | 0
LESS: | TDS (INCOME-TAX) | [5 empty] | 0
LESS: | TDS (WORKS CONTRACT TAX) | [5 empty] | 0
NET AMOUNT TO PAY | [5 empty] | Rs. | 689047
NOTE-
Certified amount for payment is Rs 6,89,047
Date | 03.05.2018 |  |  | SIGNATURE OF CHIEF ENGINEER

## GST
|  | PAN NO -AIDPA3348Q |  |  | GST No : | 27AIDPA3348Q1Z1
ARN NO -AD270320007254O
TAX INVOICE(ORIGINAL )
Tax Invoice No : 05/20-21
Date of Tax Invoice : 22-04-2020
| Reverse charge | NO
| State | Maharashtra |  |  |  | Code | 27
M/s Mindspace Business Parks Pvt Ltd -SEZ |  |  |  | PO No. |  | 4800131518
Formerly Serene Properties Pvt Ltd |  |  |  | PO date |  | 09.09.2019
Plot NO 3 , KTTC Industrial Area |  |  |  | Bldg No |  | GD-SEZ -AIROLI
Airoli , Opp. Airoli Station |  |  |  | Place of Supply |  | Maharashtra
Navi Mumbai - 400 708
GST NO :- 27AAHCS8388M2ZC
| Sub: | Ser-PHE works in PW |  | ( WORK DONE - FEB. 2020 )
Sr. No | HSN/SAC | Description work | Quantity | Unit | Rate | Gross Value | Discount/abatement | Amount
Ser-Fire Fighting works in PW
10 | 995462 | PITC of CPVC pipe- 15 mm dia | 5 | M | 190 | 950 |  | 950
20 | 995462 | PITC of CPVC Pipe - 20 mm dia | 35 | M | 250 | 8750 |  | 8750
30 | 995462 | PITC of CPVC Pipe - 25 mm dia | 45 | M | 350 | 15750 |  | 15750
40 | 995462 | PITC of Forged Brass Ball Valve -20mm | 5 | NOS | 660 | 3300 |  | 3300
50 | 995462 | PITC of Forged Brass Ball Valve -25 mm | 1 | NOS | 845 | 845 |  | 845
60 | 995462 | PITC of Water Meter | 5 | NOS | 3700 | 18500 |  | 18500
70 | 995462 | PITC of PRV Station- 25 mm dia | 1 | NOS | 4500 | 4500 |  | 4500
80 | 995462 | PITC of UPVC Pipe - 6 kg -110 mm dia | 10 | M | 540 | 5400 |  | 5400
90 | 995462 | PITC of UPVC Pipe - 6 kg -160 mm dia | 30 | M | 1350 | 40500 |  | 40500
100 | 995462 | PITC of PVC Gully Trap | 3 | NOS | 4500 | 13500 |  | 13500
110 | 995462 | PITC of Multi Floor Trap | 5 | NOS | 1250 | 6250 |  | 6250
120 | 995462 | PITC of PVC Nahani Trap 110 mm dia | 1 | NOS | 550 | 550 |  | 550
|  | Total | [5 empty] | 118795
Total Invoice amount in words | [7 empty] | 118795
(Rupees ONE LAKH EIGHTEEN THOUSAND SEVEN HUNDRED NINTY FIVE ONLY ) |  |  |  | Add CGST |  |  |  | 0
|  |  |  | Add SGST |  |  |  | 0
|  |  |  | Add IGST |  |  |  | 0
|  |  |  | Total amount after tax |  |  |  | 118795
|  |  |  | GST on reverse charge |  |  |  | NO
DESCRIPTION OF SERVICE -
9954- Construction services
| 995461 | Electrical installation services including Electrical
& fitting services, fire alarm installation services,
fire alarm installation services, burglar alarm system
installation services.
| 995462 | Water plumbing and drain laying services
PF NO. : MHBAN1617262000
ESIC NO. : 31001067220000699
1 | Services Rendered Within SEZ
2 | Services Rendered to SEZ Developers M/s Mindspace Business Parks Pvt Ltd - SEZ , Vide Gazetted Notification No 1355 ,& File No S.O. 1876(E) dt 2/11/2017 LOA 2/94/2005 EPZ dt 23.10.2006
3 | Address :- Mindspace , Opp Airoli Railyway Station , Plot No 3 , MIDC . Industrial area ,
Thane Belapur Road , Airoli , Navi Mumbai - 400 708
4 | Invoice Raised for the service rendered after date of SEZ Notification 02-11-2007.
5 | Supply to SEZ Developers for authorised operations under Bond or Letter of undertaking without payment of integrated tax
FOR B-TECH ENGINEERING
( Authorised Signatory )

## measurement sheet
MEASUREMENT SHEET
M/s Mindspace Business Parks Pvt Ltd -SEZ | [5 empty] | Date : 22-04-2020
Formerly Serene Properties Pvt Ltd | [5 empty] | PO No. |  | 4800131518
Airoli , Opp. Airoli Station | [5 empty] | PO date |  | 09.09.2019
116972 B-TECH ENGINEERING- bill details - GD-SEZ , Airoli | [5 empty] | Bill No :- 05/20-21
PO No | Description of work | HSN/SAC | PO Qty | Unit | WORK DONE QTY. |  |  | CHALLAN NO.
4800131518 | Ser-Fire Fighting works in PW |  |  |  | Previous | Persent Qty. | Total Qty.
10 | PITC of CPVC pipe- 15 mm dia | 995462 | 5 | M | 3 | 2 | 5 | 19035/1
20 | PITC of CPVC Pipe - 20 mm dia | 995462 | 35 | M | 21 | 14 | 35 | 19035/2
30 | PITC of CPVC Pipe - 25 mm dia | 995462 | 45 | M | 27 | 18 | 45 | 19035/3
40 | PITC of Forged Brass Ball Valve -20mm | 995462 | 5 | NOS | 3 | 2 | 5 | 19035/4
50 | PITC of Forged Brass Ball Valve -25 mm | 995462 | 1 | NOS | 0.6 | 0.4 | 1 | 19035/5
60 | PITC of Water Meter | 995462 | 5 | NOS | 3 | 2 | 5 | 19052/1
70 | PITC of PRV Station- 25 mm dia | 995462 | 1 | NOS | 0.6 | 0.4 | 1 | 19035/6
80 | PITC of UPVC Pipe - 6 kg -110 mm dia | 995462 | 10 | M | 6 | 4 | 10 | 19035/7
90 | PITC of UPVC Pipe - 6 kg -160 mm dia | 995462 | 30 | M | 18 | 12 | 30 | 19035/8
100 | PITC of PVC Gully Trap | 995462 | 3 | NOS | 1.8 | 1.2 | 3 | 19035/9
110 | PITC of Multi Floor Trap | 995462 | 5 | NOS | 3 | 2 | 5 | 19035/10
120 | PITC of PVC Nahani Trap 110 mm dia | 995462 | 1 | NOS | 0.6 | 0.4 | 1 | 19035/12

## ADVANCE
ADVANCE TAX INVOICE
M/s Mindspace Business Parks Pvt Ltd -SEZ |  |  |  | Date 30-09.2019
Formerly Serene Properties Pvt Ltd |  |  |  | PO No | 4800131518
Plot NO 3 , KTTC Industrial Area |  |  |  | PO Date | 09.09.2019
Airoli , Opp. Airoli Station |  |  |  | Bldg no | GD-SEZ - Airoli
Navi Mumbai - 400 708
GST NO :- 27AAHCS8388M2ZC
Sub:- ADVANCE AGAINST MATERIAL DELIVERY FOR GD-SEZ - AIROLI
Dear Sir.
Request of advance payment against material delivery for GD-SEZ - Airoli
( Encl challans & BOQ - annexure herewith )
You are requested to release the payment at the earliest.
This advance will be deducted proportionately in interim RA bills
Customer Name | PO No | PO amount | Amount payable against advance |  | Amount in word
M/S MINDSPACE BUSINESS PARKS PVT LTD -SEZ | 4800131520 | 118795 | 118795 |  | Seventy One thousand two hundred seventy seven Rupees only
Thanks & Regards,
PAN No. : AIDPA3348Q
GSTIN No. : 27AIDPA3348Q1Z1
PF NO. : MHBAN1617262000
ESIC NO. : 31001067220000699
ARN NO : AD270719000198W
for B-TECH ENGINEERING
Authorised Signatory